## Dashboard
PROJECT REPORTING DASHBOARD
DATE | TOTAL ITERATION | 2 | SPRINT 1 START DATE | ITERATION DURATION | 1.5 days | SPRINT 2 START DATE | Team Size
Note:- To view the Burndown chart for a particular day the next day should be selected in the Sprint Progress dropdown. For viewing the complete Sprint Burndown chart the status should be set to completed in the dropdown

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
1 | 1 | US 09 | As a user, I want to view the cards added by me, so that I can do the payment | MUST HAVE | 3 | Durgaprasad | 2- In Progress
2 | 2 | US 10 | As a user, I should be able to do payment for my orders so that my orders are delivered | MUST HAVE | 3 | Durgaprasad | 2- In Progress
Note on F1: Kindly refrain from providing more than 8 points to user stories

## Sprint I Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 26 | 11 | 9 | 6
SPRINT 1 BACKLOG
US-09 | T1 | Coding API layer | 2022-07-05 | 2022-07-07 | Durgaprasad | Coding | 2- In Progress | 5 | 2 | 2 | 1
| T2 | Coding Repository layer | 2022-07-05 | 2022-07-07 | Durgaprasad | Coding | 3- Completed | 0 | 0 | 0 | 0
| T3 | Coding Service layer | 2022-07-05 | 2022-07-07 | Durgaprasad | Coding | 2- In Progress | 0 | 0 | 0 | 0
| T4 | Unit testing | 2022-07-05 | 2022-07-07 | Durgaprasad | Unit Test | 2- In Progress | 6 | 3 | 2 | 1
| T5 | Maven Build | 2022-07-05 | 2022-07-07 | Durgaprasad | Build | 2- In Progress | 2 | 1 | 1 | 0
US-10 | T1 | Coding API layer | 2022-07-05 | 2022-07-07 | Durgaprasad | Coding | 2- In Progress | 4 | 2 | 1 | 1
| T2 | Coding Repository layer | 2022-07-05 | 2022-07-07 | Durgaprasad | Coding | 2- In Progress | 0 | 0 | 0 | 0
| T3 | Coding Service layer | 2022-07-05 | 2022-07-07 | Durgaprasad | Coding | 2- In Progress | 3 | 1 | 1 | 1
| T4 | Unit testing | 2022-07-05 | 2022-07-07 | Durgaprasad | Unit Test | 2- In Progress | 3 | 1 | 1 | 1
| T5 | Maven Build | 2022-07-05 | 2022-07-07 | Durgaprasad | Build | 2- In Progress | 3 | 1 | 1 | 1
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work

## Stand up Meeting
Sprint | US ID | Day | Assigned To | Points Discussed | Impediments | Action Taken

## Reference Data
SPRINT I BURN-DOWN CHART DATA
Sprint | Day | Planned | Actual | TEAM VELOCITY CHART
1 | 0 | 26 | 20
| 1 | 17.33 | 11 | Sprint | Planned | Actual
| 2 | 8.66 | 9 | 1 | 26 | 20
| 3 | 2.88 | 0
Note on E6: Effort hours pending after day 1 of sprint 1
Note on E7: Effort hours pending after day 2 of sprint 1
Note on H7: Planned hours of effort in Sprint 1
Note on I7: Story points completed in sprint 1